## start-from-scratch
Sprint 2 Tasks
Group Name: Team 6
Task Names | Sub-tasks | Person | Status | Date Completed
Player | Player States, Player Classes, Player Projectiles, Player Input | Luke | Done | 2022-02-19
Subitems | Name | Owner | Status | Date
| Player States |  | Done | 2022-02-19
| Player Classes |  | Done | 2022-02-19
| Player Projectiles |  | Done | 2022-02-19
| Player Input |  | Done | 2022-02-19
Projectile | Projectile Classes, Projectile Input | Craig | Done | 2022-02-20
Subitems | Name | Owner | Status | Date
| Projectile Classes |  | Done | 2022-02-18
| Projectile Input |  | Done | 2022-02-18
Items | Item Classes, Item Input | Austin | Done | 2022-02-18
Subitems | Name | Owner | Status | Date
| Item Classes |  | Done | 2022-02-18
| Item Input |  | Done | 2022-02-18
Tiles | Tile Classes, Tile Input | Ting | Done | 2022-02-18
Subitems | Name | Owner | Status | Date
| Tile Classes |  | Done | 2022-02-21
| Tile Input |  | Done | 2022-02-21
Enemies | Enemy Classes, Enemy Input | Zening | Done | 2022-02-21
Subitems | Name | Owner | Status | Date
| Enemy Classes |  | Done | 2022-02-21
| Enemy Input |  | Done | 2022-02-21
Refactoring | Tile Refactoring, Player Refactoring, Projectile Refactoring, Enemy Refactoring | All | Done | 2022-02-21
Subitems | Name | Owner | Status | Date
| Tile Refactoring | Ting | Done | 2022-02-20
| Player Refactoring | Luke | Done | 2022-02-20
| Projectile Refactoring | Craig | Done | 2022-02-21
| Enemy Refactoring | Zening | Done | 2022-02-21
Code Reviews | Ting, Austin, Luke, Zening, Craig |  | Done | 2022-02-21
Subitems | Name | Owner | Status | Date
| Tiles | Zening | Done | 2022-02-21
| Items | Craig | Done | 2022-02-21
| Player | Austin | Done | 2022-02-21
| Enemies | Luke | Done | 2022-02-21
| Projectiles | Ting | Done | 2022-02-21
Other | Reflection, README, Task Board |  | Done
Subitems | Name | Owner | Status | Date
| Reflection | Luke | Done | 2022-02-21
| README | Luke | Done | 2022-02-21
| Task Board | Ting | Done | 2022-02-21
2022-02-14 to 2022-02-21